## Initial Plan
Steps/Consideration | Goal | Action/Notes | LOE | Purpose | Stage | Assigned | In Progress | Complete | Not Started Yet | Next in Line
google analytics training | Better informed analytics and SEO decision making | Michael working on dashboard specific to careers, not sure how to target careers and not whole site | 2 | Measure | 1-Plan/Research | Angela, Heidi, Bryce, Michael |  | ongoing
analytics | filter out internal IPs | Michael to compare with IT to determine if accurately represented | 2 | Measure | 1-Plan/Research | Michael |  | SF
google analytics - set measurable goals page-update- and post-page-update | Clear picture of what we can measure against for success and/or changes (1) schedule of google analytics review, particularly heatmap, advise on engagement issues (2) document results we can measure now to compare against later | setup snapshots of to compare to: users, sessions, time on-site, bounce rate, application completions, HubSpot form submissions. Michael working on reorganizing for what we need and changes discussed ITS, documenting analytics with each improvement, e.g., chat, page, update, app update, etc. | 3 | Measure | 1-Plan/Research | Michael |  | SF
Short simple application - easy apply, quick response | Increase applicants by ??%, quick response process in place | Changes gathered and documented. Michael to confirm and adjust if needed | 2 | UX/UI | 1-Plan/Research | Angela |  | SF
A/B testing on careers page | heat mapping determined side bar, video and quotes are not being clicked on | Wireframe complete and in design/mockup stage for new page | 3 | Measure | 1-Plan/Research | Heidi/Kelly |  | X
evaluate single vs separate site SEO (e.g., HubSpot blog) |  | For SEO purposes, my research indicates that a single-site is far superior. Michael determined we can house HubSpot blog and still stay on same domain | 2 | Measure | 1-Plan/Research | Angela |  | X
Familiarity with application process from start to hire/not hire, description of what to expect, quick response to candidate, provide stages of hiring process | walk through user journey to get full impact of what applicants experience, improve entire experience, rewrite emails, add links to useful info | Completed application process review with HR, documented in BC | 4 | UX/UI | 1-Plan/Research | Team |  | X
google analytics - heat mapping, | Review and implement and begin measuring (www.crazyegg.com) | in place - what do we need to analyze and report/learn from | 2 | Measure | 1-Plan/Research | Michael |  | X
google analytics - research existing settings and determine what can be changed and/or enhanced | Review and implement all required analytics and begin measuring (www.crazyegg.com) | Angela reviewing regularly and reporting in basecamp | 3 | Measure | 1-Plan/Research | Michael |  | X
Map out user journey | Clear understanding of the visitor so that content can be targeted for the best user experience, engagement and CTA | Use wireframe to map journey and develop plan for promoting new page | 3 | UX/UI | 1-Plan/Research | Alex/Heidi |  | X
Measure, determine if candidates are going to website before or after interview scheduling | Web site informs candidate prior to application, better informed for interview | determined that most are likely visiting site first | 2 | Measure | 1-Plan/Research | Angela |  | X
Technology/integrations - Newton | confirm all works as it does now, or better | next step - sandbox for testing | 5 | Functionality | 1-Plan/Research | Michael |  | X
Define and target visitor by type/skills (professional vs entry level) | Direct visitor to target info with less clicks and/or browsing, CTA apply for job that matches skills | Determined what will be used for careers website - execution TBD | 2 | Inform | 2-Wireframe | Angela/Michael |  | X
Cross reference from recs to more info on careers site | Well informed applicants | Link to careers site form rec - not possible with Indeed, but possible via JS | 1 | UX/UI | 2-Wireframe | Michael |  | SF
Most candidates don’t know what company does | clear picture of what company does prior to application | Content - company reputation, career progression, culture, work environment, teams and roles, diversity and inclusion, community. (implemented in WF) | 2 | Inform | 2-Wireframe | Angela (prelim. content), Alex (WF) |  | SF
Convince visitor that careers at company is a good move | CTA: apply for job that matches skills |  | 2 | Inform | 2-Wireframe | Angela (prelim. content)/Alex (WF) |  | x
If not convinced, direct to FAQ and/or communications sign up - CTA: opt-in | If skills don’t match available jobs, encourage and bring visitor back for repeat visits | Get with HR to start building out a FAQ Q/A list - saved in MC Archive jobs | 2 | Inform | 2-Wireframe | Angela |  | X
Inform applicants about company and job details before interview | lessen no shows and reduce time for recruiters | Is their a HR script that we can edit? | 3 | Inform | 2-Wireframe | Angela, Alex (WF) |  | X
Make company more SEO friendly | SEO rich | factor in content | 3 | Improved search | 3-Content Plan | TBD | SF
Use AdSearch to evaluate what search terms are used to find our site or similar | Add metadata that matches popular search within our site | Ongoing, visit each meeting to see if there is anything we need to factor in for final site |  | Improved search | 3-Content Plan | Michael | X
Frequent content changes - job highlights, etc. | Content calendar, management and follow-through |  | 3 | Continued Engagement | 3-Content Plan | Angela, Laura |  |  | X
Overall content plan | better informed applicants for job/interview (ween out the not-really interested, decrease no-shows) | Answer why clearly: 1. why, 2. company values, 3. employer reputation, 4. career progression, 5. work environment, 6. team and roles, 7. diversity & inclusion, 8. community giving, 9. WIIFM (what's in it for me), 10. show n tell, 11. easy apply, 12. what to expect https://rallyrecruitmentmarketing.com/learn/12-features-of-an-appealing-careers-page/ | 5 | Inform | 3-Content Plan | Angela, Laura |  |  | X
Write copy for site | SEO rich | Research and include with final copy |  | Inform | 3-Content Plan | Angela/Laura |  |  | X
More video content | increase engagement by ??% | how are career videos tagged in DAM, gather and put in gallery for review, discuss and list opportunities for new | 2 | Inform | 3-Content Plan | Angela/Heidi |  | X
Cross reference from FAQ's to other pages in site |  |  | 2 | UX/UI | 3-Mockup |  | X
Add micro interactions throughout | Aid in guiding user in website experience, encourage lingering to interact for visitors | Revisit once mockup is complete | 4 | UX/UI | 3-Mockup | Alex |  |  |  | X
Factor in company updated brand guidelines, adapt for digital/user experience and B2T (talent) audience (vs B2B audience) | Brand that is uses digital and marketing best practices | TBD | 3 | UX/UI | 3-Mockup | Designer |  |  | X
Show diversity with content rather than direct statement | Show that we are diverse in hiring (race, disabled, veterans) | Add throughout site, show hiring disabled reward and similar substantiations | 3 | UX/UI | 3-Mockup |  |  | X
Functionality plan | Develop "once" with a mapped out plan, end process is easy to make changes for all involved | Michael working on documentation data from WF | 4 | Continued Engagement | 4-Front End Dev | Michael, Bryce, Heidi, Alex |  | SF
html, styling, interactivity |  | TBD | 4 | UX/UI | 4-Front End Dev | Michael, Alex |  |  | X
Address and tackle negative Indeed remarks | Improve company reputation in community and search results, improve SEO so other positive results show up first | working on 3 more surveys for 2019, Indeed - answer FAQ as verified associates - weigh in higher than Joe Blow answering. | 4 | Inform | 5-Marketing Plan | Angela supporting HR with this initiative - ongoing | SF
HubSpot form | increase form submissions and segmentation of submission for targeted email communications | Form in place, need to build out workflow | 3 | Target content | 5-Marketing Plan | Angela | SF
Make company look ligament and reputable for google business listings |  | Claim google business listings to ensure accuracy | 3 | Continued Engagement | 5-Marketing Plan | Angela | SF
Make company look ligament and reputable for recruiting sites |  | Updated company page for Indeed (85% complete), Glass door (not started), etc., | 3 | Continued Engagement | 5-Marketing Plan | Angela | SF
Expand email marketing plan, targeted communications, flow, segments, personalization (HubSpot or CM) | More opt-in and increased repeat visits for job that match skills |  | 4 | Continued Engagement | 5-Marketing Plan | Heidi, Angela, Laura |  |  | X
Marketing Plan to direct visitors to careers site: Traditional (20%) vs Digital (80%) | Marketing plan that is well balanced and hits all markets | TBD Later | 4 | Continued Engagement | 5-Marketing Plan | Angela, Laura |  |  | X
Review links in auto response emails and make sure they are relevant and content doesn't change to be not relevant | links in communications direct to pages that are always relevant | Completed update of auto response email with job-seeker friendly content and relevant links. | 2 | Continued Engagement | 5-Marketing Plan | Angela |  | X
Maintain associate referral program, ongoing flow of candidates, content/collateral calendar | Decrease recruiting expenses and efforts "on demand" | TBD Later | 4 | Continued Engagement | 6-Maintaince Plan | Angela, Laura |  |  | X

## Timeline
Milestone | Date
1-Plan/Research | 2018-11-15
2-Wireframe | 2018-12-15
3-Content Plan | 2018-12-30
3-Functionality Plan | 2018-12-30
3-Mockup | 2018-01-01
4-Front End Dev | 2018-02-01
4-Back End Dev | 2018-02-02
5-Marketing Plan | 2018-02-03
6-Maintaince Plan | 2018-03-01
Launch date | TBD