## Meeting input Results (hidden)
Feature | Top | Group Specific | Considerations | Buckets
Mobile | x |  | Mobile first, limited desktop for call centers | Backend/Functionality
Access - based on schedule |  |  | Concerns: schedules change daily | Backend/Functionality
Calendar |  |  | Add-to-calendar feature | Backend/Functionality
Content push/pull |  |  | Consider: Scheduled, timed vs. interrupt | Backend/Functionality
Electronic Signature pull |  |  |  | Backend/Functionality
Facebook/AC direct connections |  |  | Concerns: social during work hours | Backend/Functionality
Offsite access |  |  |  | Backend/Functionality
Profile update |  |  | email, phone, skills, certifications, career profile | Backend/Functionality
Real time updates |  |  |  | Backend/Functionality
Reminders (Handbook Update) |  | HR, Team leads |  | Backend/Functionality
Reminders (MoTrak, MoTime) |  |  |  | Backend/Functionality
Schedule - RSVP, Event Tools |  |  |  | Backend/Functionality
Set as default home page company-wide |  |  | Consider: GM Computers, non-standard associates | Backend/Functionality
Signoff |  |  | Resources with signoff | Backend/Functionality
Single sign on |  |  |  | Backend/Functionality
Subscribe/Unsubscribe Options |  |  |  | Backend/Functionality
Communications (Team-Specific) | xx |  | Consider: GM equipment, process for Mgrs. to take important info to floor | Communication - Dept Specific
Alerts (Weather) |  |  |  | Communication - Dept Specific
Client happenings |  | Roadside |  | Communication - Dept Specific
Industry/Client related info |  | Roadside | weather, travel delays, etc. | Communication - Dept Specific
Info Buckets |  |  | Buckets of info available for specific purpose e.g. Agents, new hires, etc. (digital version would allow linking in multiple places) | Communication - Dept Specific
Communications (Company-wide) | x |  | Growl, new business, awards, community events, scholarships, charity, etc. | Communication - Need to know
Access to Key/Important info quickly |  |  | Warm fuzzy stuff secondary | Communication - Need to know
Alerts (Company-wide) |  |  | weather, | Communication - Need to know
Alerts (Department) |  |  | Reboot required, etc. | Communication - Need to know
Alerts (Weather) |  |  | for snow days, also for vehicle services | Communication - Need to know
Floorplans |  |  |  | Communication - Need to know
Communications (Facilities) | x |  | fridge cleanup, parking. etc. | Communication - Nice to know
Communications (HR) | x |  |  | Communication - Nice to know
Handbook | x |  | searchable, TOC/Bookmarks, quick links, printable | Communication - Nice to know
Communications (Executive) |  |  |  | Communication - Nice to know
Communications (IT) |  |  |  | Communication - Nice to know
Communications (MoFit) |  |  | Inspiration, recipes, exercise, events, opt-out, refer quickly after original posting | Communication - Nice to know
Communications (New Hires/Associates leave) |  |  | Security/daily updates | Communication - Nice to know
Communications (Promotions) |  |  | Include Write Up | Communication - Nice to know
Events recording |  |  | Associates that can't participate due to schedule | Communication - Nice to know
Messaging |  |  | Show online, away, out, etc., Concerns: needs to be monitored (skype used already and has to be monitored) | Communication - Nice to know
MoList/MoSwap |  |  | Craig's List, sell, list, events, rides, etc. | Communication - Nice to know
Morley Careers |  |  |  | Communication - Nice to know
Social - Focus groups |  |  | Motorcyclists, MoFit, etc. | Communication - Nice to know
Associate Directory | x |  | searchable, works in all browsers, includes photo, building, dept, etc., auto complete, direct reports, more robust | Tools
Support Request (Helpdesk/IT) | x |  | Also include tips solutions for common problems | Tools
One Stop | xxx |  | MoTime, MoTrak, DMU, MAPP, Registration Program configuration, SalesForce, Newton, Paycor, Client Tools (Roadside, etc.) | Tools
FAQ |  |  |  | Tools
Morley Forms (Accounting) |  |  | Submission to roles, vs. people | Tools
Morley Forms (DMU) |  |  |  | Tools
Morley Forms (HR) |  |  |  | Tools
Morley Forms (Onboarding/Orientation) |  |  | Include additional resources, videos, downloadables, etc. | Tools
Morleynet |  |  |  | Tools
Org Chart |  |  | Hierarchy - reports, subordinates | Tools
Overview (Company) |  |  | scripted text for "What is Morley" | Tools
Overview (Department) |  |  | Include additional resources, videos, downloadables, etc. Also, acronym spell out (TAC, RVDC) | Tools
Resume Upload |  |  | Searchable by management | Tools
Search |  |  |  | Tools
Service Request (IT) |  |  |  | Tools
Service Request (ITS) |  |  |  | Tools
Upload |  |  | ability to upload content, resources, make updates | Tools
Vacation time |  |  | available/used, real-time | Tools
Who to contact for what |  |  |  | Tools
Access - non-standard associates |  | Warehouse, Fabricators, Call Center | Computer not part of day-to-day, no email access, Kiosks? | UI/UX
Department-level Tools Access |  |  | Consider: screen space, default screen size | UI/UX
Fun factor |  |  | easter eggs built in, scavenger, etc. | UI/UX
Interactivity |  |  |  | UI/UX
Organized, clear |  |  |  | UI/UX
Usability |  |  | Static/fixed toolbar - access from anywhere | UI/UX
Usability - color scheme |  |  | gray text - hard to read | UI/UX
Usability - speed |  |  | full optimization for fast load, including mobile | UI/UX
User friendly |  |  |  | UI/UX

## AC Master Plan - Phase 1
Task | Notes | Milestone | Team | Assigned | Dependency | Est. Hours | Due Date | Complete
Content - Content Strategy | Determine buckets | Content | Writing | Laura, P |  |  |  | x
Site Plan - Main messaging | Write main messaging of main content (Header,CTA) | Messaging | Writing | Lisa | Content Strategy |  |  | x
Site Plan - Main messaging | Determine quick access links | Messaging | Writing | Lisa | Content Strategy |  |  | x
Site Plan - Main messaging | Write messaging of secondary content (Header,CTA) | Messaging | Writing | Lisa | Content Strategy |  |  | x
Content Inventory | Reuse vs new | Messaging | Writing | Lisa | Content Strategy |  |  | x
Content - Home |  | Gather/Write Content | Writing | Lisa |  |  | 2016-08-19 | x
Content - Careers |  | Gather/Write Content | Writing | Lisa |  |  | 2016-08-19 | x
Content - Support Services |  | Gather/Write Content | Writing | Lisa |  |  | 2016-08-26 | x
Content - Associate Hightlights |  | Gather/Write Content | Writing | Lisa |  |  | 2016-08-26 | x
Content - FAQ |  | Gather/Write Content | Writing | Lisa |  |  | 2016-09-02 | x
Content - About Company |  | Gather/Write Content | Writing | Lisa |  |  | 2016-09-02 | x
Content - Benefits & Policies |  | Gather/Write Content | Writing | Lisa |  |  | 2016-09-07 | x
Content - Calendar |  | Gather/Write Content | Writing | Lisa |  |  | 2016-09-07 | x
Content - MoSwap |  | Gather/Write Content | Writing | Lisa |  |  | 2019-09-09 | x
Content - Ektron content load - Home |  | Load Content | Writing | Lisa, Heidi, Chris, Alecia | Working environment in Ektron |  |  | x
Content - Ektron content load - Careers |  | Load Content | Writing | Lisa, Heidi, Chris, Alecia | Working environment in Ektron |  |  | x
Content - Ektron content load - Support Services |  | Load Content | Writing | Lisa, Heidi, Chris, Alecia | Working environment in Ektron |  |  | x
Content - Ektron content load - Associate Hightlights |  | Load Content | Writing | Lisa, Heidi, Chris, Alecia | Working environment in Ektron |  |  | x
Content - Ektron content load - FAQ |  | Load Content | Writing | Lisa, Heidi, Chris, Alecia | Working environment in Ektron |  |  | x
Content - Ektron content load - About Company |  | Load Content | Writing | Lisa, Heidi, Chris, Alecia | Working environment in Ektron |  |  | x
Content - Ektron content load - Benefits & Policies |  | Load Content | Writing | Lisa, Heidi, Chris, Alecia | Working environment in Ektron |  |  | x
Content - Ektron content load - Calendar |  | Load Content | Writing | Lisa, Heidi, Chris, Alecia | Working environment in Ektron |  |  | x
Content - Ektron content load - MoSwap |  | Load Content | Writing | Lisa, Heidi, Chris, Alecia | Working environment in Ektron |  |  | x
0
Design - UI Style Guide | imagery, nav, color, typography, buttons, hover, icons, etc. | Visual Design | Design |  | User testing - Detail Wireframe - Content |  | 2016-08-26 | x
Design - Visual Mockup - Home |  | Visual Design | Design |  | User testing - Detail Wireframe - Content |  | 2016-08-26 | x
Design - Visual Mockup - Careers |  | Visual Design | Design |  | User testing - Detail Wireframe - Content |  | 2016-09-02 | x
Design - Visual Mockup - Support Services |  | Visual Design | Design |  | User testing - Detail Wireframe - Content |  | 2016-09-02 | x
Design - Visual Mockup - Associate Highlights |  | Visual Design | Design |  | User testing - Detail Wireframe - Content |  | 2016-09-02 | x
Design - Visual Mockup - FAQ |  | Visual Design | Design |  | User testing - Detail Wireframe - Content |  | 2016-09-02 | x
Design - Visual Mockup - About Company |  | Visual Design | Design |  | User testing - Detail Wireframe - Content |  | 2016-09-09 | x
Design - Visual Mockup - Benefits & Policies |  | Visual Design | Design |  | User testing - Detail Wireframe - Content |  | 2016-09-09 | x
Design - Visual Mockup - Calendar |  | Visual Design | Design |  | User testing - Detail Wireframe - Content |  | 2016-09-09 | x
Design - Visual Mockup - MoSwap |  | Visual Design | Design |  | User testing - Detail Wireframe - Content |  | 2016-09-09 | x
Requirements Gathering - grid system |  | Project Definition | UX/UI | Heidi | - | 3 |  | x
Site Plan - Content Wireframe - top | Begin blocking in top content | Site Architecture | UX/UI | Heidi | Content Strategy | 4 |  | x
Site Plan - Content Wireframe - one-click | Begin blocking in quick access (one-click) content | Site Architecture | UX/UI | Heidi | Content Strategy | 4 |  | x
Site Plan - Content Wireframe - muitiple-click | Begin blocking in secondary (two-clicks or more) content | Site Architecture | UX/UI | Heidi | Content Strategy | 4 |  | x
Site Plan - Build Sitemap |  | Site Architecture | UX/UI | Heidi | Site Plan - Content Wireframe Approval | 12 |  | x
Site Plan - Simple Wireframe | walkthrough, basic functionality | Site Testing | UX/UI | Heidi | Site Plan - Content Wireframe Approval | 12 |  | x
Site Plan - Detail Wireframe | Detailed wireframe/walkthrough of each page and functionality for main | Site Plan/Functionality | UX/UI | Heidi | Site Plan - Simple Wireframe - Approvals / User Testing | 16 |  | x
Site Plan - Detail Wireframe - user testing |  | Site Testing | UX/UI | All | Site Plan - Detail Wireframe - Approvals | 12 |  | x
Site Plan - Detail Wireframe - Responsive |  | Site Plan/Functionality | UX/UI | Heidi | User Testing | 20 |  | 4
UI - Grid framework, templated structure | page, header, hav, content, footer, etc. | Site Build | UX/UI | Heidi | Site Plan - Detail Wireframe - Approvals / User Testing | 30 | 2016-09-02 | x
UI - Styling - incorporate Design UI Style guide | imagery, nav, color, typography, buttons, hover, icons, etc. | Site Build | UX/UI | Heidi | Design - UI Style Guide | 20 | 2016-09-02 | x
Content - begin styling content - Home |  | Site Build | UX/UI | Heidi | Approved design/content for Home | 10 | 2016-09-09 | x
Content - begin styling content - MoSwap |  | Site Build | UX/UI | Heidi | Approved design/content for MoSwap | 10 | 2016-09-09 | x
Content - begin styling content - Careers |  | Site Build | UX/UI | Heidi | Approved design/content for Careers | 10 | 2016-09-09 | x
Content - begin styling content - Support Services |  | Site Build | UX/UI | Heidi | Approved design/content for Support Services | 10 | 2016-09-09 | x
Content - begin styling content - Associate Highlights |  | Site Build | UX/UI | Heidi | Approved design/content for Associate Highlights | 10 | 2016-09-09 | x
Content - begin styling content - FAQ |  | Site Build |  | Heidi | Approved design/content for Support FAQ | 10 | 2016-09-09 | x
Content - begin styling content - About Company |  | Site Build | UX/UI | Heidi | Approved design/content for About Company | 20 | 2016-09-16 | x
Content - begin styling content - Benefits & Policies |  | Site Build |  | Heidi | Approved design/content for Benfits & Policies | 30 | 2016-09-16 | x
Content - begin styling content - Calendar |  | Site Build | UX/UI | Heidi | Approved design/content for Calendar | 10 | 2016-09-16 | x
[6 empty] | 257 |  | 4
ESG - Newton job feed |  |  |  |  | Meeting with ESG |  |  | x
ESG - confirm which database fields update upon moves/promotions and terminations |  |  |  |  | Meeting with ESG |  |  | x
|  | Current forms to digital | Dev | Matt, Bryce | SSO | 8 | 2016-07-05 | x
Determine logical path for execution of various functionality components |  | Logic Diagram | Dev | Bryce, Josh | Data Object Diagram | 10 | 2016-07-05 | x
Prototype functions and methods |  | Logic Diagram | Dev | Bryce, Josh | Data Object Diagram | 8 | 2016-07-05 | x
Determine logic path for overall functionality of the application as a whole |  | Logic Diagram | Dev | Bryce, Josh | Data Object Diagram | 10 | 2016-07-05 | x
Map out methods, functions, and helper services visually to determine what data is being pulled from what models and when data transactions are necessary |  | Logic Diagram | Dev | Bryce, Josh | Data Object Diagram | 8 | 2016-07-05 | x
Review and Adjust based on changing requirements / roadblocks and hurdles presented during initial code buildout |  | Logic Diagram | Dev | Bryce, Josh | Data Object Diagram | 10 | 2016-07-05 | x
Review Logic Charts with Team |  | Logic Diagram | Dev | Bryce, Josh | Data Object Diagram | 1 | 2016-07-05 | x
Finalize Logic Diagram |  | Logic Diagram | Dev | Bryce, Josh | Data Object Diagram | 1 | 2016-07-05 | x
Implement on/off network detection |  | Online/Offline User Status | Dev | Matt, Bryce | SSO | 4 | 2016-07-05 | x
Implement view for managers to see which employees are online / offline |  | Online/Offline User Status | Dev | Matt, Bryce | SSO | 6 | 2016-07-05 | x
Identify permissions groups and level of access necessary |  | Permissions | Dev | Bryce, Josh | Logic Diagram | 1 | 2016-07-05 | x
Implement Calendar View to see events, holidays, P&B, MoFit - add filters, default to all. Add pagination per month to view, add structure for color coding event types. Calendar data to be fed via database or API |  | RSVP / Event Calendar | Dev | Bryce, Josh | SSO | 6 | 2016-07-05 | x
Add to Calendar |  | RSVP / Event Calendar | Dev | Josh | SSO | 4 | 2016-07-05 | x
Permissions -Group / Role |  | RSVP / Event Calendar | Dev | Bryce | SSO | 4 | 2016-07-05 | x
Reporting |  | RSVP / Event Calendar | Dev | Bryce | SSO | 6 | 2016-07-05 | x
Confirm and Implement appropriate security controls to maintain Security Compliance |  | Security Requirements | Dev | Bryce, Josh | Logic Diagram | 8 | 2016-07-05 | x
Research analytics platforms for internal sites |  | Site Analytics | Dev | Josh | SSO | 8 | 2016-07-05 | x
Implement analytics code / tagging |  | Site Analytics | Dev | Josh | SSO | 6 | 2016-07-05 | x
Implement Sign-on based off of logging into network from machine |  | SSO | Dev | Bryce | Logic Diagram | 4 | 2016-07-05 | x
Determine any additional SSO implementations for various tools and sites (e.g. 401k) |  | SSO | Dev | Bryce, Josh | Logic Diagram | 2 | 2016-07-05 | x
Implement Web Form |  | Suggestion Box Form | Dev | Matt, Bryce | SSO | 8 | 2016-07-05 | x
Determine Backend Frameworks to use for Application |  | Technology Requirements | Dev | Bryce, Josh | Logic Diagram | 2 | 2016-07-05 | x
Determine Frontend Frameworks to use for Application |  | Technology Requirements | Dev | Bryce, Josh | Logic Diagram / Backend Framework Decision | 2 | 2016-07-05 | x
Implement Transactional Email service |  | Weekly Digest Corporate Communications | Dev | Josh | SSO | 10 | 2016-07-05 | x
Searchable |  | User Profiles | Dev | Josh | SSO, Communication Groups Implentation, Database Implementation | 8 | 2016-07-11 | x
Ability to add user-defined content (Moderated before viewable) as well as opt-in options for things like MoFit |  | User Profiles | Dev | Matt, Bryce | SSO, Communication Groups Implentation, Database Implementation | 8 | 2016-07-12 | x
Auto-Populated with Company Information (MoTime) |  | User Profiles | Dev | Bryce | SSO, Communication Groups Implentation, Database Implementation | 2 | 2016-07-12 | x
Implement blog rolls for various internal topics / newsletters |  | Blogs | Dev | Josh | SSO, Ektron API Implementation | 8 | 2016-07-14 | x
Implement Opt-in/Opt-out/Subscribe/Unsubscribe to blogs |  | Blogs | Dev | Bryce | SSO, Ektron API Implementation, Blog Roll Implementation | 4 | 2016-07-14 | x
Implement Blog Archiving for later viewing |  | Blogs | Dev | Josh | SSO, Ektron API Implementation, Blog Roll Implementation | 6 | 2016-07-15 | x
Determine using SignalR / Long Polling for content updates |  | Real-time Content Updates | Dev | Bryce | SSO, Ektron API Implementation, Blog Roll Implementation | 24 | 2016-07-19 | x
Implement Cron Job to send out email with that weeks updates automatically |  | Weekly Digest Corporate Communications | Dev | Matt, Josh | SSO, Ektron API Implementation, Blog Roll Implementation | 4 | 2016-07-20 | x
Implement top-down org chart |  | Organization Chart | Dev | Bryce, Josh | SSO, Logic Diagram | 14 | 2016-07-26 | x
dynamically generate chart based on primary / secondary managers |  | Organization Chart | Dev | Bryce, Josh | SSO, Logic Diagram | 4 | 2016-07-27 | x
Requirements / Review current solution |  | RSVP / Event Calendar | Dev | Josh | SSO, Logic Diagram | 2 | 2016-07-27 | x
Determine proper API / Feed for internal job postings |  | Internal Job Postings | Dev | Bryce, Josh | SSO, Logic Diagram, ESG - Newton job feed | 3 | 2016-07-28 | x
Implement job posting view that consumes feed correctly |  | Internal Job Postings | Dev | Bryce | SSO, Logic Diagram, ESG - Newton job feed | 6 | 2016-07-28 | x
Implement overall functionality to be utilized throughout site |  | Opt-in/Opt-out/Subscribe/UnsubscribeNon-essential | Dev | Bryce | SSO, Opt-in / Opt-Out implementation for blogs | 8 | 2016-07-29 | x
Determine different types of notifications |  | Notifications | Dev | Bryce, Josh | SSO, SignalR Implementation | 2 | 2016-08-02 | x
Implement notifications with real-time updating |  | Notifications | Dev | Matt, Bryce | SSO, SignalR Implementation | 8 | 2016-08-02 | x
Create Webservice to pull approved content to news feed |  | Real-time Content Updates | Dev | Matt, Bryce | SSO, SignalR Implementation | 12 | 2016-08-03 | x
Create Notification functionality to automatically notify users of new content being available (with ability to manually refresh content from news feed with the latest available) |  | Real-time Content Updates | Dev | Matt, Bryce | SSO, SignalR Implementation | 10 | 2016-08-04 | x
Create View to show full communication that links from news feed |  | Real-time Content Updates | Dev | Matt, Josh | SSO, SignalR Implementation | 3 | 2016-08-04 | x
Create Filter functionality for news feed |  | Real-time Content Updates | Dev | Josh | SignalR Implementation, News Feed | 4 | 2016-08-04 | x
Implement web services / notification functionality |  | Real-time Content Updates | Dev | Matt, Bryce | SSO, SignalR Implementation | 12 | 2016-08-05 | x
Define Auto-Reminder / Auto-Notification requirements for integration with other tools |  | Reminders / Notifications | Dev | Josh | SSO, SignalR Implementation | 6 | 2016-08-08 | x
Implement New Job Notifications |  | Reminders / Notifications | Dev | Josh | SSO, SignalR Implementation | 4 | 2016-08-08 | x
Implement notification / reminder service |  | Reminders / Notifications | Dev | Matt,Bryce | SSO, SignalR Implementation | 6 | 2016-08-08 | x
Implement Auto Notification |  | Anniversaries / Promotions / Terminations / Transfers | Dev | Bryce | SSO, SignalR Implementation, Notification Implementation, Alert Implementation | 6 | 2016-08-09 | x
Implement data return to be displayed on sidebar |  | Anniversaries / Promotions / Terminations / Transfers | Dev | Bryce | SSO, SignalR Implementation, Notification Implementation, Alert Implementation | 2 | 2016-08-09 | x
Real-time results display |  | Polling Functionality | Dev | Bryce | SSO, SignalR Implementation, Notification Implementation, Alert Implementation | 8 | 2016-08-09 | x
Target Polling |  | Polling Functionality | Dev | Matt, Bryce | SSO, SignalR Implementation, Notification Implementation, Alert Implementation, Communication Groups | 8 | 2016-08-10 | x
Polling Reporting |  | Polling Functionality | Dev | Matt,Bryce | SSO, SignalR Implementation, Notification Implementation, Alert Implementation, Communication Groups | 8 | 2016-08-10 | x
Implement alert system |  | Alerts | Dev | Matt, Bryce | SSO, SignalR Implementation, Notification System Implementation | 6 | 2016-08-11 | x
Implement view to see alerts / notifications received |  | Notification / Alert Dashboard | Dev | Matt, Bryce | SSO, SignalR Implementation, Notification System Implementation, Alert System Implementation | 6 | 2016-08-12 | x
Implement Admin View to send out notifications / alerts manually |  | Notification / Alert Dashboard | Dev | Bryce | SSO, SignalR Implementation, Notification System Implementation, Alert System Implementation | 6 | 2016-08-12 | x
Associate Directory - Search by name, bus unit - Implement grid view for displaying results |  | Associate Directory | Dev | Josh | SSO | 8 | 2016-08-15 | x
Implement Web Form - Display feed of approved associate recognitions. Provide approval flow for proofing purposes |  | Associate Recognition Form | Dev | Matt, Bryce | SSO, Transactional Email Implementation | 6 | 2016-08-15
Add FAQ section with in page search - track search questions to build intelligent search algorithms to provide results based question patterns. |  | FAQs | Dev | Josh |  | 9 | 2016-08-16 | x
Implement Video / Photo Gallery functionality -- potentially pull this from the DAM system as opposed to Amazon S3 |  | Video / Photo Gallery | Dev | Josh | SSO | 8 | 2016-08-16 | x
Determine potential data points that require data models |  | Data Object Diagram | Dev | Bryce, Josh |  | 3 | 2016-09-12 | x
|  | Testing | Dev | Bryce, Josh |  | 8 | 2016-09-12 | x
Map out properties for each data model |  | Data Object Diagram | Dev | Bryce, Josh |  | 5 | 2016-09-13 | x
Determine parent -> child relationship |  | Data Object Diagram | Dev | Bryce, Josh |  | 3 | 2016-09-13 | x
Determine 1-to-1, 1-to-Many, Many-to-Many, and Many-to-1 relationships between objects for database architecture |  | Data Object Diagram | Dev | Bryce, Josh |  | 4 | 2016-09-13 | x
Diagram objects and relationships |  | Data Object Diagram | Dev | Bryce, Josh |  | 8 | 2016-09-14 | x
Review Diagram |  | Data Object Diagram | Dev | Bryce, Josh |  | 1 | 2016-09-15 | x
Adjust based on changes to requirements |  | Data Object Diagram | Dev | Bryce, Josh |  | 3 | 2016-09-15 | x
Finalize models |  | Data Object Diagram | Dev | Bryce, Josh |  | 2 | 2016-09-15 | x
Determine functionality requirements based off of user feedback |  | Functionality Requirements | Dev | Bryce, Josh |  | 4 | 2016-09-15 | x
Review and confirm understanding of functionality requirements |  | Functionality Requirements | Dev | Bryce, Josh |  | 2 | 2016-09-15 | x
Finalize requirements and breakdown into Application "Phases" |  | Functionality Requirements | Dev | Bryce, Josh |  | 2 | 2016-09-16 | x
Implement permissions groups |  | Permissions | Dev | Bryce, Josh |  | 6 | 2016-09-16 | x
Research Available Search Platforms |  | Search | Dev | Bryce, Josh |  | 8 | 2016-09-19 | x
Implement Search Analytics |  | Search | Dev | Josh |  | 8 | 2016-09-20 | x
Implement Search |  | Search | Dev | Josh |  | 12 | 2016-09-22 | x
Review Implementation |  | Search | Dev | Bryce, Josh |  | 1 | 2016-09-23 | x
Debug Implementation |  | Search | Dev | Bryce, Josh |  | 4 | 2016-09-23 | x
Finalize for Deployment |  | Search | Dev | Bryce, Josh |  | 1 | 2016-09-23 | x
|  | Testing | Dev | Matt, Bryce, Josh |  | 8 | 2016-09-26 | x
Confirm Database Server Requirements |  | Technology Requirements | Dev | Bryce, Josh |  | 1 | 2016-09-27 | x
Confirm Hardware Requirements |  | Technology Requirements | Dev | Bryce, Josh |  | 1 | 2016-09-27 | x
Confirm OS of Server |  | Technology Requirements | Dev | Bryce, Josh |  | 1 | 2016-09-27 | x
Create web Form |  | Associate Referal | Dev | Bryce, Josh |  | 4 | 2016-09-25 | x
[6 empty] | 482 |  | 0
Default page load - Monitor and optimized (multiple steps throughout) |  | Site Optimization | Final Testing | Heidi | Pages in place along with functionality

## AC Master Plan - Phase 2
Category | Task | Phase | Assigned | Est. Hours | Due Date | Hours to Date
Home | Content Update Strategy |  | Lisa |  | TBD | TBD
Benefits & Polices | Content Update Strategy |  | Lisa |  | TBD | TBD
Support | Content Update Strategy |  | Lisa |  | TBD | TBD
FAQ | Content Update Strategy |  | Lisa |  | TBD | TBD
Calendar | Content Update Strategy |  | Lisa |  | TBD | TBD
Morley | Content Update Strategy |  | Lisa |  | TBD | TBD
Careers | Content Update Strategy |  | Lisa |  | TBD | TBD
Associates | Content Update Strategy |  | Lisa |  | TBD | TBD
Benefits & Polices | Handbook - Visual Mockup |  |  |  | TBD | TBD
Benefits & Polices | Handbook - Styling |  | Heidi | 10 | TBD | TBD
Hours Total |  |  |  | 10 | TBD | TBD
Messaging | Meetings - TBD |  | Lisa/P |  | TBD | TBD
Calendar | Morley Event Updates | 1.1 | Josh | 35 | TBD | TBD
Suggestion Form | Develop | 1.1 | Matt | 15 | TBD | TBD
Data | Company Data Revamp | 1.1 |  |  | TBD | TBD
Messaging | Posts / Messaging / Notification revamp | 1.2 |  |  | TBD | TBD
Account/Login | Single Sign-On | 1.3 |  |  | TBD | TBD
Search | Site Search | 1.4 |  | 40 | TBD | TBD
Photos | Gallery Updates | 2 |  | 20 | TBD | TBD
Videos | Gallery Updates | 2 |  | 20 | TBD | TBD
Optimization | Default page load - Monitor and optimized (multiple steps throughout) |  | Heidi/Josh/Bryce |  | TBD | TBD